Date: 26/08/2026

Present: KM, WN, LPE, FG & JNJ

Subject: CIS Accreditation Preparation – Service Projects Showcase

1. Purpose & Scope

Review school service activities to identify and select key evidence to showcase to the CIS accreditation team.

2. Key Projects & Activities Identified

- Core Definitions: Activities designated by the school and performed by teachers and students.

- Residential Projects:

    - Year 8: Kambui

    - Year 10: Malewa

    - Year 12: Residential RS

- Other Showcase Highlights:

- Wednesday Service Learning Projects.

- Karen Popcorn Sale (funds used to buy printers).

- Yearbook and bulletin articles.

- Annual events: Christmas Buckets, Christmas Fair and Less for More.

- Parents' contributions: Ol-tepesi project (kitchen, toilet and classroom) and Golf Fundraising events.

- Alumni highlights (specifically featuring Michelle Muturi).

- CMT & Board involvement ( photo of Ravi at Kiambogo).

- Scope Requirement: Must represent through-school activities across both campuses.

3. Content Packaging & Presentation Strategy

- Format Target: 3-minute final presentation video.

- Media Assets: Combine photos and articles directly from the school yearbook alongside video coverage explaining all service projects.

- Storage & Coordination:

- Create a shared Google Folder to collect all projects and assets.

- Use Google Docs for ongoing team communication.

4. Division of Roles

| Stakeholder / Area | Responsible Person(s) | Key Deliverables & Actions |
| --- | --- | --- |
| Alumni | KM | Collect relevant alumni materials ( Michelle Muturi). |
| Learners | JNJ & FG | Gather student project evidence. |
| Presentation Coordination | LPE | Work with KM to finalize the presentation. |
| PTA & Board | WN | Source evidence for PTA and Board involvement. |
| Staff | LPE | Source evidence of staff participation. |
| Content Filtering | LPE & KM (All Area Leads) | Identify and narrow down key media into designated sections; source as many relevant photos and videos as possible. |

5. Timeline & Key Deadlines

- Friday, 4th September: All required resources and assets compiled.

- Wednesday, 9th September: All evidence gathered, submitted in the drive, and agreed upon by the team.

- Friday, 11th September: Final completed presentation turned in.